## Sheet1
RommieConnect
Group Members
Name | Student Number | Student ID:
Sampreet Klair | 145031225 | sklair2@myseneca.ca
Harsahbaj Singh | 146457221 | hsna27@myseneca.ca
Ritish Sharma | 146407226 | rsharma360@myseneca.ca
Risk Identification Matrix
Risk ID | Risk Name | Description |  |  | Risk Owner
R001 | Resource Availability | Key team members may be unavailable during critical phases, causing delays in the project timeline. |  |  | Project Manager
R002 | Budget Overrun | The project may exceed the allocated budget of $60,000 due to unforeseen expenses. |  |  | Finance Team
R003 | Technical Integration | Challenges in integrating backend systems, such as the matching algorithm, could delay project completion. |  |  | Lead Developer
R004 | User Adoption | The platform may fail to attract a sufficient number of users, affecting its success. |  |  | Marketing Team
R005 | Data Security Breach | Sensitive user data could be compromised, leading to legal issues and loss of trust. |  |  | Security Team
R006 | Regulatory Compliance | Failure to comply with legal regulations could result in fines and project delays. |  |  | Legal Team
R007 | Technology Obsolescence | Rapid changes in technology may render some of the chosen tools or frameworks obsolete before completion. |  |  | Lead Developer
R008 | Vendor Reliability | Issues with third-party vendors could cause delays or compromise quality. |  |  | Procurement
R009 | User Feedback Delays | Delayed or insufficient user feedback may lead to inadequate features being developed. |  |  | QA Specialist
R010 | Project Scope Creep | Uncontrolled changes or additions to the project scope could lead to delays and budget overruns. |  |  | Project Manager
Qualitative Risk Analysis Matrix
Risk ID | Risk Name | Impact (Consequence) | Probability of Occurrence | Priority
R001 | Resource Availability | High | Medium | High
R002 | Budget Overrun | High | Medium | High
R003 | Technical Integration | High | High | Very High
R004 | User Adoption | High | Medium | High
R005 | Data Security Breach | Very High | Low | High
R006 | Regulatory Compliance | Medium | Low | Medium
R007 | Technology Obsolescence | Medium | Medium | Medium
R008 | Vendor Reliability | Medium | Medium | Medium
R009 | User Feedback Delays | Medium | Medium | Medium
R010 | Project Scope Creep | High | Medium | High
Prioritized Risk List
Priority Order | Risk ID | Risk Name | Impact | Probability | Graph Placement
1 | R003 | Technical Integration | High | High | Top Right (Critical)
2 | R001 | Resource Availability | High | Medium | Upper Middle
3 | R002 | Budget Overrun | High | Medium | Upper Middle
4 | R004 | User Adoption | High | Medium | Upper Middle
5 | R005 | Data Security Breach | Very High | Low | Top Left (Watch)
6 | R010 | Project Scope Creep | High | Medium | Upper Middle
7 | R007 | Technology Obsolescence | Medium | Medium | Center
8 | R008 | Vendor Reliability | Medium | Medium | Center
9 | R009 | User Feedback Delays | Medium | Medium | Center
10 | R006 | Regulatory Compliance | Medium | Low | Bottom Left (Low Priority)
Graph Placement
Risk ID | Risk Name | Impact (Consequence) | Likelihood (Probability of Occurrence)
R003 | Technical Integration | 3 | 3
R001 | Resource Availability | 3 | 2
R002 | Budget Overrun | 3 | 2
R004 | User Adoption | 3 | 2
R005 | Data Security Breach | 4 | 1
R010 | Project Scope Creep | 3 | 2
R007 | Technology Obsolescence | 2 | 2
R008 | Vendor Reliability | 2 | 2
R009 | User Feedback Delays | 2 | 2
R006 | Regulatory Compliance | 2 | 1
Quantitative Risk Analysis and Risk Factor
Risk ID | Risk Name | Impact (Consequence) | Likelihood (Probability of Occurrence) | Risk Factor
R003 | Technical Integration | 3 | 3 | 9
R001 | Resource Availability | 3 | 2 | 6
R002 | Budget Overrun | 3 | 2 | 6
R004 | User Adoption | 3 | 2 | 6
R010 | Project Scope Creep | 3 | 2 | 6
R005 | Data Security Breach | 4 | 1 | 4
R007 | Technology Obsolescence | 2 | 2 | 4
R008 | Vendor Reliability | 2 | 2 | 4
R009 | User Feedback Delays | 2 | 2 | 4
R006 | Regulatory Compliance | 2 | 1 | 2
Quantified Risk Analysis and Prioritization
Priority Order | Risk ID | Risk Name | Impact (Consequence) | Likelihood (Probability of Occurrence) | Risk Factor
1 | R003 | Technical Integration | 3 | 3 | 9
2 | R001 | Resource Availability | 3 | 2 | 6
3 | R002 | Budget Overrun | 3 | 2 | 6
4 | R004 | User Adoption | 3 | 2 | 6
5 | R010 | Project Scope Creep | 3 | 2 | 6
6 | R005 | Data Security Breach | 4 | 1 | 4
7 | R007 | Technology Obsolescence | 2 | 2 | 4
8 | R008 | Vendor Reliability | 2 | 2 | 4
9 | R008 | User Feedback Delays | 2 | 2 | 4
10 | R006 | Regulatory Compliance | 2 | 1 | 2
Risk Response Plans
Risk ID | Risk Name | Risk Response Strategy | Actions |  | Contingency Plan
R003 | Technical Integration | Mitigate | - Conduct thorough integration testing. |  | - Adjust project timeline if issues are unresolved.
|  |  | - Hire specialized integration consultants. |  | - Implement a phased rollout to deliver parts of the system while continuing integration work on remaining parts.
- Create a detailed integration plan.
R001 | Resource Availability | Mitigate | - Cross-train team members. |  | - Hire temporary staff if resources are unavailable for an extended period.
|  |  | - Create a resource management plan. |  | - Adjust project timelines as needed to accommodate resource shortages.
- Use external contractors or consultants if necessary.
R002 | Budget Overrun | Mitigate | - Implement strict budget tracking. |  | - Request additional funding if necessary.
|  |  | - Identify cost-saving opportunities. |  | - Revise the project scope to reduce costs if budget overruns are likely.
- Negotiate with vendors for better rates or flexible payment terms.