## Sheet1
WBS | Task Name | Duration | Resource
1 | Requirement Analysis | 3 days
1.1 | Deploy Project Charter | 2 days | Product Manager
1.2 | Deploy Preliminary Project Scope Statement | 3 days | Product Manager
2 | RFP and Vendor Selection | 4 days
2.1 | Create Request for Proposal | 2 days | Product Manager
2.2 | Shortlist Vendor for Circulation | 3 days | Product Manager
2.3 | RFP Consolidation and Analysis | 4 days | Product Manager
2.4 | Finalize Vendor | 4 days | Product Manager
2.5 | Project Kickoff Meeting | 2 days | Product Manager
2.6 | Design Phase Complete | 2 days | UI/UX Designer
3 | Implementation | 12 days
3.1 | Functional Specification Document (FSD) | 12 days | Developer
3.2 | Technical Specification Document (TSD) | 11 days | Developer
4 | Acceptance Testing | 4 days
4.1 | Start the Testing | 4 days
4.1.1 | Create Test Cases | 3 days | QA Tester
4.1.2 | Test the given Program | 4 days | QA Tester
4.2 | Test Feedback | 4 days
4.2.1 | Analyze the Tests and give feedback | 4 days | QA Tester
5 | Deployment | 3 days
5.1 | Creating the online environment for submission | 3 days | Developer
5.2 | Deploying the project online | 2 days | QA Tester
6 | Training and Handover | 3 days
6.1 | Begin the training of newly hired professionals | 3 days | Human Resource
6.2 | Handover the work to newly trained professionals | 3 days | Human Resource

## Sheet2
WBS | Task Name | Duration
1 | Requirement Analysis
1.1 | Deploy Project Charter
1.2 | Deploy Preliminary Project Scope Statement
2 | RFP and Vendor Selection
2.1 | Create Request for Proposal
2.2 | Shortlist Vendor for Circulation
2.3 | RFP Consolidation and Analysis
2.4 | Finalize Vendor
2.5 | Projeect Kickoff Meeting
2.6 | Design Phase Complete
3 | Implementation
3.1 | Functional Specification Document (FSD)
3.2 | Technical Specification Document (TSD)
4 | Acceptance Testing
4.1 | Start the Testing
4.2 | Test Feedback
5 | Deployment
5.1 | Creating the online environment for submission
5.2 | Deploying the project online
6 | Training and Handover
6.1 | Begin the training of newly hired professionals
6.2 | Handover the work to newly trained professionals

## Sheet3
WBS | Task Name | Duration
0 | Plan for Coporate Website Development
1 | Requirement Analysis
2 | RFP and Vendor Selection
3 | Implementation
4 | Acceptance Testing
5 | Deployment
6 | Training and Handover