## Working route
Blackboard Group No 01 Class ZEE | Project Planning |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Last Chance Submission
SMART goals ==> | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific tasks and WBS | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING TESTING (not) DONE DONE LATE HUNG UP
reference and relative due dates |  |  |  | 2023-07-27 | Wednesday Jul.26 |  |  |  | 9 | days |  |  |  | 14 | days |  |  |  | 21 | days | Latest possible submission is last day of classes; late penalties apply at 20% per day after your Version 3 due date: | 2023-08-17
Each Team member | Co-ordinating with members, understanding each members views, landing on common solutions and dividing equal tasks to get the project done before deadline. | Share with team by uploading notes/documents to Bb 01 team channel's Files | Realistic planned hours : 2 hrs actual hours : 1:45 hrs | Planned date & Time of delivery: 26 July Actual date : 26 July | DONE | Co-ordinating with members, understanding each members views, landing on common solutions and complete their own module to get the project done before deadline. | Share with team by uploading notes, test cases and code to Bb 01 team channel's Files | Realistic planned hours: 2 hrs. | Planned date & Time of delivery: Aug.1 | TO DO | co-ordinating with members, understanding each members views, landing on common solutions and complete their own module to get the project done before deadline. | Share with team by uploading notes, test cases and code to Bb 01 team channel's Files | realistic planned hours: 1.5 hrs. | Monday Aug.7 | TO DO | co-ordinating with members, understanding each members views, landing on common solutions and complete their own module to get the project done before deadline. | Share with team by uploading notes, test cases and code to Bb 01 team channel's Files | realistic planned hours: 1.5 hrs. | Thursday Aug.10 | TO DO
Team Meeting Agenda ==> | Discussing about project, checking project status targeting problems faced, sharing files, requesting review from professor if needed. | Deliverable is considered: all the work done before deadline agreed: Project Plan excel file, Minutes of Meeting Word file | Realistic planned hours : 2 hrs actual hours : 1:25 hrs | Saturday Jul.29 | DONE | Discussing about project, checking individual code module status targeting problems faced, refine Plan, sharing files, requesting review from professor if needed. | Deliverable is considered: all the work done before deadline agreed: C Code, Test cases, Project Plan excel file, Minutes of Meeting Word file | Realistic planned hours: 5 hrs (2 hrs + 3 hrs) | Wednesday Aug.2 | TO DO | discussing about project, checking individual code module status targeting problems faced, refine Plan, sharing files, requesting review from professor if needed. | deliverable is considered: all the work done before deadline agreed: C Code, Test cases, Project Plan excel file, Minutes of Meeting Word file | realistic planned hours: 4 hrs (2 hrs + 2 hrs) | Monday Aug.7 | TO DO | discussing about project, checking individual code module status targeting problems faced, refine Plan, sharing files, requesting review from professor if needed. | deliverable is considered: all the work done before deadline agreed: C Code, Test cases, Project Plan excel file, Minutes of Meeting Word file | realistic planned hours: 4 hrs (2 hrs + 2 hrs) | Friday Aug.11 | TO DO | Submit final version of artefacts from Teams to Blackboard in a .ZIP archive. Backup Team's files. | updated all DONE items with actual hours. |  | Friday Aug.11 | TO DO
| Request review from professor (if needed) | Sharing the file with the professor and asking for the views. | n/a | Saturday Jul.29 | DONE | request review from professor (if needed) | Sharing the file with the professor and asking for the views. | To be done. | Wednesday Aug.2 | TO DO | request review from professor (if needed) | Sharing the file with the professor and asking for the views. | To be done. | Monday Aug.7 | TO DO | request review from professor (if needed) | Sharing the file with the professor and asking for the views. | To be done. | Friday Aug.11 | TO DO |  |  |  |  | TO DO
Prince Prince Fundamentals | Declaring group deadlines, planning meetings, estimating required meeting time | Submitting expected time for each work to be done, planning the meetings ahead to be on schedule, Creating and finalizing the Project Plan, also fulfilled the specific tasks assigned. | Realistic planned hours : 2:30 hrs actual hours : 2 hrs | Saturday Jul.29 | DONE | Review and running the code provided, adding comments where needed, creating and running test cases for the Fundamentals C code. | Writing the code, compiling and testing. Making test cases and sending to Team Leader for further process. | Realistic planned hours: 7 hrs. | Thursday Aug.3 | TO DO | Adding the version 2 code to already submitted version 1 code, running and compiling it, adding comments where needed, creating and running test cases for the newly added Fundamentals C code. | Updating the fundamentals code file by adding version 2 code, compiling and testing. Making test cases and sending to Team Leader for further process. | Realistic planned hours: 5 hrs | Tuesday Aug.8 | TO DO | Adding the version 3 code to already submitted version 1 and version 2 code, running and compiling it, adding comments where needed, creating and running test cases for the newly added Fundamentals C code. | Updating the Fundamentals code file by adding version 3 code, compiling and testing. Making test cases and sending to Team Leader for further process. | Realistic planned hours: 5 hrs | Saturday Aug.12 | TO DO |  |  |  | Saturday Aug.12 | TO DO
Fenil Soni Manipulations | Managing files, keeping record of group submissions. | Submitting expected time for each work to be done, planning the meetings ahead to be on schedule, Creating and finalizing the Project Plan, also fulfilled the specific tasks assigned. | Realistic planned hours : 3hrs actual hours : 2 hrs | Saturday Jul.29 | DONE | Review and running the code provided, adding comments where needed, creating and running test cases for the Manipulations C code. | Writing the code, compiling and testing. Making test cases and sending to Team Leader for further process. | Realistic planned hours: 7 hrs. | Thursday Aug.3 | TO DO | Adding the version 2 code to already submitted version 1 code, running and compiling it, adding comments where needed, creating and running test cases for the newly added Manupulations C code. | Updating the Manipulations code file by adding version 2 code, compiling and testing. Making test cases and sending to Team Leader for further process. | Realistic planned hours: 5 hrs | Tuesday Aug.8 | TO DO | Adding the version 3 code to already submitted version 1 and version 2 code, running and compiling it, adding comments where needed, creating and running test cases for the newly added Manipulation C code. | Updating the Manipulations code file by adding version 3 code, compiling and testing. Making test cases and sending to Team Leader for further process. | Realistic planned hours: 5 hrs | Saturday Aug.12 | TO DO |  |  |  | Saturday Aug.13 | TO DO
Manav Zadafiya Tokenizing | Creating MS Teams, adding members, taking charge whether everyone is possible to attend meeting, supplying required information. | Submitting expected time for each work to be done, planning the meetings ahead to be on schedule, Creating and finalizing the Project Plan, also fulfilled the specific tasks assigned. | Realistic planned hours : 3:30 hrs actual hours : 2:20 hrs | Saturday Jul.29 | DONE | Review and running the code provided, adding comments where needed, creating and running test cases for the Tokenizing C code. | Writing the code, compiling and testing. Making test cases and sending to Team Leader for further process. | Realistic planned hours: 7 hrs. | Thursday Aug.3 | TO DO | Adding the version 2 code to already submitted version 1 code, running and compiling it, adding comments where needed, creating and running test cases for the newly added Tokenizing C code. | Updating the Tokenizing code file by adding version 2 code, compiling and testing. Making test cases and sending to Team Leader for further process. | Realistic planned hours: 5 hrs | Tuesday Aug.8 | TO DO | Adding the version 3 code to already submitted version 1 and version 2 code, running and compiling it, adding comments where needed, creating and running test cases for the newly added Tokenizing C code. | Updating the Tokenizing code file by adding version 3 code, compiling and testing. Making test cases and sending to Team Leader for further process. | Realistic planned hours: 5 hrs | Saturday Aug.12 | TO DO |  |  |  | Saturday Aug.14 | TO DO
Sampreet Klair Conversions Team Leader | Group leader: managing group, helping everyone, hosting meetings and finalising project | Submitting expected time for each work to be done, planning the meetings ahead to be on schedule, Creating and finalizing the Project Plan, fulfilled the specific tasks assigned and combining the work of each team member | Realistic planned hours : 3 hrs actual hours : 2:30 hrs | Sunday Jul.30 | DONE | Review and running the code provided, adding comments where needed, creating and running test cases for the Conversion C code. | Writing the code, compiling and testing. Making test cases and reviewing the Test cases provided by other team members and finalizing the project version 1. | Realistic planned hours: 7 hrs. | Friday Aug.4 | TO DO | Adding the version 2 code to already submitted version 1 code, running and compiling it, adding comments where needed, creating and running test cases for the newly added Conversaions C code. | Updating the Conversions code file by adding version 2 code, compiling and testing. Making test cases and reviewing the Test cases provided by other team members and finalizing the project version 2. | Realistic planned hours: 5 hrs | Wednesday Aug.9 | TO DO | Adding the version 3 code to already submitted version 1 and version 2 code, running and compiling it, adding comments where needed, creating and running test cases for the newly added Conversions C code. | Updating the Conversions code file by adding version 3 code, compiling and testing. Making test cases and reviewing the Test cases provided by other team members and finalizing the project version 3. | Realistic planned hours: 5 hrs | Sunday Aug.13 | TO DO |  |  |  | Sunday Aug.13 | TO DO
|  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | milestone upload to Blackboard |  |  |  |  | DUE DATE upload to Blackboard |  |  |  |  | ABSOLUTE DEADLINE
[19 empty] | submissions after this date subject to extra time charge of 20% per day |  |  |  |  | no submissions accepted after this date
Note on A1: Update ?? to your Blackboard group number and XYY to your CPR101XYY class code. Then press TAB to next set up item in E3.
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: work in progress: an objective or task according to a Time based target – hours of effort will be completed by a due date & time TESTING: work promoted by team member after Doing to other team members for Testing/Measurement. DONE: an objective or task Tested/Measured as completed. Only Team leader can change status to DONE (or back to DOING for rework or HUNG UP for problem resolution) HUNG UP: no longer doing something because it became unRealistic. Tell the team right away. E.g. hours required will not be completed by the due date-time; specific objectives were found to be too vague when Doing; no metrics were applied to measure doneness.
Note on E3: Change this to the date of your Project Management class and the worksheet will calculate all milestone dates.